## Sheet1
Task |  |  |  | Task Number/Duration |  | Time Spent | Status | Planned | In Progress | Complete | Slack
Blake Rude | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Main Menu (initial) |  |  |  | 1 | 1 | 1 | Complete | bar: Planned 1
Setting Menu (initial) |  |  |  | 2 | 1 | 1 | Complete | bar: In Progress 2 to Slack 17
In Game HUD |  |  |  | 3 | 5 |  | Planned | bar: In Progress 2 to Slack 6
in Game Tooltips |  |  |  | 4 | 5 |  | Planned | Slack 7: 3
Tutorial |  |  |  | 5 | 4 |  | Planned | Slack 12: 4
Main Menu (final) |  |  |  | 6 | 2 | 1 | In Progress | Slack 16: 5
Setting Menu (final) |  |  |  | 7 | 2 |  | Planned | Slack 18: 6, 2
Testing/Improvement |  |  |  | 8 | 5 |  | Planned | Slack 20: 7
Finalization |  |  |  | 9 | 3 |  | Planned | Slack 25: 8
Extra Work not Within Plan | [5 empty] | 2 |  | Planned 1: Setting up Git
Total |  |  |  |  | 28 | 5
Lucas Thoms | bar: Planned 1 to Slack 52
Understanding Requirements |  |  |  | 1 | 2 | 2 | Complete | bar: Planned 1 to In Progress 2
Determining Weapon Characteristics |  |  |  | 2 | 2 | 2 | Complete | bar: Planned 1 to In Progress 2
Determining Ammo Characteristics |  |  |  | 3 | 2 | 2 | Complete | bar: Planned 1 to In Progress 2
Gathering Weapon and Ammo Assets |  |  |  | 4 | 4 | 3 | In Progress | Complete 3: 2,3
Programming Weapon Distribution |  |  |  | 5 | 3 | 0 | In Progress | Slack 7: 4
Programming Ammo Distribution |  |  |  | 6 | 3 |  | Planned | Slack 7: 4
Programming Ammo Pickup/Exchange |  |  |  | 7 | 6 |  | Planned | Slack 10: 6
Programming Weapon Loading |  |  |  | 8 | 6 |  | Planned | Slack 16: 5,7
Programming Weapon Firing |  |  |  | 9 | 6 |  | Planned | Slack 22: 8
Programming Weapon Aiming |  |  |  | 10 | 6 |  | Planned | Slack 16: 5
Documentation |  |  |  | 11 | 4 |  | Planned | bar: Planned 1 to Slack 4
Developing Tests |  |  |  | 12 | 4 | bar: Planned 1 to Slack 4
Extra Work not Within Plan | [5 empty] | 3 |  | Planned 1: Integrating MVP
Total |  |  |  |  | 48 | 12
Max Icardo | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Sound/Music Collection |  |  |  | 1 | 1 |  | planned | bar: 1
Event Decode |  |  |  | 2 | 1 |  | planned | bar: 2
Audio Control |  |  |  | 3 | 1 |  | planned | 3: 2
Testing |  |  |  | 4 | 2 |  | planned | 4: 3
Merging |  |  |  | 5 | 1 |  | planned | 6: 4
Extra Work not Within Plan
Total |  |  |  |  | 6 | 0
Noah Mammen
Research |  |  |  | 1 | 6 | 4 | In Progress | bar: 1 to 6
Find/Make Network Interface |  |  |  | 2 | 6 |  | Planned | bar: 7 to 9
Implement Interface |  |  |  | 3 | 5 |  | Planned | [12 empty] | 2
Team Meetings |  |  |  | 4 | 16 | 6 | In Progress
Planning/Diagrams |  |  |  | 5 | 6 | 3 | in Progress
Programming |  |  |  | 6 | 20 |  | Planned | [17 empty] | 3,5
Intermittent Integration |  |  |  | 7 | 3 |  | Planned | [37 empty] | 5, 6
Testing |  |  |  | 8 | 3 |  | Planned | [37 empty] | 6
Final Product Implementation |  |  |  | 9 | 4 |  | Planned | [40 empty] | 4, 7, 8
Extra Work not Within Plan
Total |  |  |  |  | 69 | 13
Yingruo Liu
Requirements Collection |  |  |  | 1 | 1 | 1 | Complete | bar: 1
World Design and Finalization |  |  |  | 2 | 2 | 2 | Complete | bar: 2 to 3
Skeleton/Draft in 3D |  |  |  | 3 | 14 | 4 | In Progress | 4: 2
Visual Refinement |  |  |  | 4 | 12 | 0 | Planned | [17 empty] | 3
Programming |  |  |  | 5 | 23 |  | Planned | [17 empty] | 3
Testing |  |  |  | 6 | 7 |  | Planned | [38 empty] | 5
User Documentation |  |  |  | 7 | 5 |  | Planned | [45 empty] | 6
Installation |  |  |  | 8 | 2 |  | Planned | [52 empty] | 7
Extra Work not Within Plan | [5 empty] | 3 | [58 empty] | 8
Total |  |  |  |  | 66 | 10
Kiran
Meet and Greet | 6 attendees |  | RFP meeting | 3 attendees |  | Group Meeting 1 | 6 attendees | 2: Group meeting 2; 3: 5 attendees
6 |  |  | 6 |  |  | 15 |  | 2: 5
[8 empty] | Budget | Actual | Delta
[7 empty] | Programming | 1: 21700; 2: 4000; 3: -17700
[7 empty] | Meetings | 1: 4800; 2: 3800; 3: -1000
Complete total : |  | 72 | hours |  |  |  | Total | 1: 26500; 2: 7800; 3: -18700; 8: S
|  | 7200 | dollars
| Date | Jan 30th | Feb 10th | Feb 12th | Feb 25th
| Topic | Meet and Greet | RFP | Champion | Unity Set up
| Hours |  | 3 | 3 | 1
| Lucas | 1 | 3 | 3 | 1
| Blake | 1 | 3 | 3 | 1
| Noah | 1 |  | 3 | 1
| Max | 1 |  | 3 | 1
| Yingruo | 1 | 3 | 3 | 1
| Kiran | 1 |  | 3
| Total | 6 | 9 | 18 | 5
| Total Cost | 600 | 900 | 1800 | 500

## Sheet2
| Date | Feb 10th | Feb 12th | Feb 25th
| Topic | RFP | Champion | Unity Set up
| Hours | 3 | 3 | 1
Lucas |  | 3 | 3
Blake |  | 3 | 3
Noah |  | 3 | 3 | 1
Max |  |  | 3
Yingruo |  | 3 | 3
Kiran |  |  | 3