## Sheet1
Task |  |  |  | Task Number/Duration |  | Time Spent | Status | Planned | In Progress | Complete | Slack
Blake Rude | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Main Menu (initial) |  |  |  | 1 | 1 | 0.5 | In Progress | bar: Planned 1
Setting Menu (initial) |  |  |  | 2 | 1 |  | Planned | bar: In Progress 2 to Slack 17
In Game HUD |  |  |  | 3 | 5 |  | Planned | bar: In Progress 2 to Slack 6
in Game Tooltips |  |  |  | 4 | 5 |  | Planned | Slack 7: 3
Tutorial |  |  |  | 5 | 4 |  | Planned | Slack 12: 4
Main Menu (final) |  |  |  | 6 | 2 |  | Planned | Slack 16: 5
Setting Menu (final) |  |  |  | 7 | 2 |  | Planned | Slack 18: 6, 2
Testing/Improvement |  |  |  | 8 | 5 |  | Planned | Slack 20: 7
Finalization |  |  |  | 9 | 3 |  | Planned | Slack 25: 8
Extra Work not Within Plan | [5 empty] | 2 |  | Planned 1: Setting up Git
Total |  |  |  |  | 28 | 2.5
Lucas Thomas | bar: Planned 1 to Slack 52
Understanding Requirements |  |  |  | 1 | 2 | 2 | Complete | bar: Planned 1 to In Progress 2
Determining Weapon Characteristics |  |  |  | 2 | 2 | 1 | In Progress | bar: Planned 1 to In Progress 2
Determining Ammo Characteristics |  |  |  | 3 | 2 | 1 | In Progress | bar: Planned 1 to In Progress 2
Gathering Weapon and Ammo Assets |  |  |  | 4 | 4 | 1 | In Progress | Complete 3: 2,3
Programming Weapon Distribution |  |  |  | 5 | 3 |  | Planned | Slack 7: 4
Programming Ammo Distribution |  |  |  | 6 | 3 |  | Planned | Slack 7: 4
Programming Ammo Pickup/Exchange |  |  |  | 7 | 6 |  | Planned | Slack 10: 6
Programming Weapon Loading |  |  |  | 8 | 6 |  | Planned | Slack 16: 5,7
Programming Weapon Firing |  |  |  | 9 | 6 |  | Planned | Slack 22: 8
Programming Weapon Aiming |  |  |  | 10 | 6 |  | Planned | Slack 16: 5
Documentation |  |  |  | 11 | 4 |  | Planned | bar: Planned 1 to Slack 4
Developing Tests |  |  |  | 12 | 4 | bar: Planned 1 to Slack 4
Extra Work not Within Plan
Total |  |  |  |  | 48 | 5
Max Icardo
Sound/Music Collection |  |  |  | 1 | 1 |  | planned | bar: Planned 1
Event Decode |  |  |  | 2 | 1 |  | planned | bar: In Progress 2
Audio Control |  |  |  | 3 | 1 |  | planned | Complete 3: 2
Testing |  |  |  | 4 | 2 |  | planned | Slack 4: 3
Merging |  |  |  | 5 | 1 |  | planned | Slack 6: 4
Extra Work not Within Plan
Total |  |  |  |  | 6 | 0
Noah Mammen
Research |  |  |  | 1 | 6 | 1.5 | In Progress | bar: Planned 1 to Slack 6
Find/Make Network Interface |  |  |  | 2 | 6 |  | Planned | bar: Slack 7 to Slack 12
Implement Interface |  |  |  | 3 | 5 |  | Planned | Slack 13: 2
Team Meetings |  |  |  | 4 | 16 |  | Planned | bar: Planned 1 to Slack 40
Planning/Diagrams |  |  |  | 5 | 6 |  | Planned | bar: Planned 1 to Slack 37
Programming |  |  |  | 6 | 20 |  | Planned | Slack 18: 3,5
Intermittent Integration |  |  |  | 7 | 3 |  | Planned | Slack 38: 5, 6
Testing |  |  |  | 8 | 3 |  | Planned | Slack 38: 6
Final Product Implementation |  |  |  | 9 | 4 |  | Planned | Slack 41: 4, 7, 8
Extra Work not Within Plan
Total |  |  |  |  | 69 | 1.5
Yingruo Liu
Requirements Collection |  |  |  | 1 | 1 | 1 | Complete | bar: Planned 1
World Design and Finalization |  |  |  | 2 | 2 | 2 | Complete | bar: In Progress 2 to Complete 3
Skeleton/Draft in 3D |  |  |  | 3 | 14 | 4 | In Progress | Slack 4: 2
Visual Refinement |  |  |  | 4 | 12 | 0 | Planned | Slack 18: 3
Programming |  |  |  | 5 | 23 |  | Planned | Slack 18: 3
Testing |  |  |  | 6 | 7 |  | Planned | Slack 39: 5
User Documentation |  |  |  | 7 | 5 |  | Planned | Slack 46: 6
Installation |  |  |  | 8 | 2 |  | Planned | Slack 53: 7
Extra Work not Within Plan | [5 empty] | 3 |  | Slack 58: 8
Total |  |  |  |  | 66 | 11
Kiran
Complete total : |  | 22.5 | 35
|  | 22500 | 35000
| Date | Feb 10th | Feb 12th | Feb 25th
| Topic | RFP | Champion | Unity Set up
| Hours | 3 | 3 | 2
Lucas |  | 3 | 3 | 2
Blake |  | 3 | 3 | 2
Noah |  |  | 3 | 2
Max |  |  | 3 | 2
Yingruo |  | 3 | 3 | 2
Kiran |  |  | 3

## Sheet2
| Date | Feb 10th | Feb 12th | Feb 25th | tbd | tbd | tbd | tbd | tbd | tbd | tbd | Total
| Topic | RFP | Champion | Unity Set up
| Hours | 3 | 3 | 2
Lucas |  | 3 | 3 | 2 | [7 empty] | 8
Blake |  |  | 3 | 2 | [7 empty] | 5
Noah |  | 3 | 3 | 2 | [7 empty] | 8
Max |  |  | 3 | 2 | [7 empty] | 5
Yingruo |  | 3 | 3 | 2 | [7 empty] | 8
Kiran |  |  | 3 | [8 empty] | 3

## Sheet3
|  | Total |  |  |  | Coding |  |  |  | Meetings |  |  |  | Systems Analysis |  |  | Overhead
|  | Budgeted | Actual | Deficit |  | Budgeted | Actual | Deficit |  | Budgeted | Actual | Deficit |  | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
| Blake | 8900 | 750 | 8150 |  | 2800 | 250 | 2550 |  | 2000 | 500 | 1500 |  | 1100 | 0 | 1100 | 3000 | 0 | 3000
| Lucas | 8900 | 1300 | 7600 |  | 2800 | 500 | 2300 |  | 2000 | 800 | 1200 |  | 1100 | 0 | 1100 | 3000 | 0 | 3000
| Max | 6700 | 500 | 6200 |  | 600 | 0 | 600 |  | 2000 | 500 | 1500 |  | 1100 | 0 | 1100 | 3000 | 0 | 3000
| Noah | 11400 | 950 | 10450 |  | 5300 | 150 | 5150 |  | 2000 | 800 | 1200 |  | 1100 | 0 | 1100 | 3000 | 0 | 3000
| Yingruo | 12700 | 1900 | 10800 |  | 6600 | 1100 | 5500 |  | 2000 | 800 | 1200 |  | 1100 | 0 | 1100 | 3000 | 0 | 3000
| Kiran | 6100 | 300 | 5800 |  | 0 | 0 | 0 |  | 2000 | 300 | 1700 |  | 1100 | 0 | 1100 | 3000 | 0 | 3000
| Total | 54700 | 5700 | 49000 |  | 18100 | 2000 | 16100 |  | 12000 | 3700 | 8300 |  | 6600 | 0 | 6600 | 18000 | 0 | 18000
| Date | Feb 10th | Feb 12th | Feb 25th | tbd | tbd | tbd | tdb | tbd | tbd | tbd | tbd | tbd | Total
| Topic | RFP | Champion | Unity Set up
| Hours | 3 | 3 | 2 | [9 empty] | 8
Lucas |  | 3 | 3 | 2 | [9 empty] | 8
Blake |  |  | 3 | 2 | [9 empty] | 5
Noah |  | 3 | 3 | 2 | [9 empty] | 8
Max |  |  | 3 | 2 | [9 empty] | 5
Yingruo |  | 3 | 3 | 2 | [9 empty] | 8
Kiran |  |  | 3 | [10 empty] | 3