## Sheet1
Task | Task Number/Duration |  | Time Spent | Status | Planned | In Progress | Complete | Slack
Blake Rude |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Main Menu (initial) | 1 | 1 | 0.5 | In Progress | bar: Planned 1
Setting Menu (initial) | 2 | 1 |  | Planned | bar: In Progress 2 to Slack 17
In Game HUD | 3 | 5 |  | Planned | bar: In Progress 2 to Slack 6
in Game Tooltips | 4 | 5 |  | Planned | Slack 7: 3
Tutorial | 5 | 4 |  | Planned | Slack 12: 4
Main Menu (final) | 6 | 2 |  | Planned | Slack 16: 5
Setting Menu (final) | 7 | 2 |  | Planned | Slack 18: 6, 2
Testing/Improvement | 8 | 5 |  | Planned | Slack 20: 7
Finalization | 9 | 3 |  | Planned | Slack 25: 8
Extra Work not Within Plan |  |  | 2 |  | Planned 1: Setting up Git
Total |  | 28 | 2.5
Lucas Thomas | bar: Planned 1 to Slack 52
Understanding Requirements | 1 | 2 | 2 | Complete | bar: Planned 1 to In Progress 2
Determining Weapon Characteristics | 2 | 2 | 1 | In Progress | bar: Planned 1 to In Progress 2
Determining Ammo Characteristics | 3 | 2 | 1 | In Progress | bar: Planned 1 to In Progress 2
Gathering Weapon and Ammo Assets | 4 | 4 | 1 | In Progress | Complete 3: 2,3
Programming Weapon Distribution | 5 | 3 |  | Planned | Slack 7: 4
Programming Ammo Distribution | 6 | 3 |  | Planned | Slack 7: 4
Programming Ammo Pickup/Exchange | 7 | 6 |  | Planned | Slack 10: 6
Programming Weapon Loading | 8 | 6 |  | Planned | Slack 16: 5,7
Programming Weapon Firing | 9 | 6 |  | Planned | Slack 22: 8
Programming Weapon Aiming | 10 | 6 |  | Planned | Slack 16: 5
Documentation | 11 | 4 |  | Planned | bar: Planned 1 to Slack 4
Developing Tests | 12 | 4 | bar: Planned 1 to Slack 4
Extra Work not Within Plan
Total |  | 48
Max Icardo
Sound/Music Collection | 1 | 1 |  | planned | bar: Planned 1
Event Decode | 2 | 1 |  | planned | bar: In Progress 2
Audio Control | 3 | 1 |  | planned | Complete 3: 2
Testing | 4 | 2 |  | planned | Slack 4: 3
Merging | 5 | 1 |  | planned | Slack 6: 4
Extra Work not Within Plan
Total |  | 6 | 0
Noah Mammen
Research | 1 | 6 | 1.5 | In Progress | bar: Planned 1 to Slack 6
Find/Make Network Interface | 2 | 6 |  | Planned | bar: Slack 7 to Slack 12
Implement Interface | 3 | 5 |  | Planned | Slack 13: 2
Team Meetings | 4 | 16 |  | Planned | bar: Planned 1 to Slack 40
Planning/Diagrams | 5 | 6 |  | Planned | bar: Planned 1 to Slack 37
Programming | 6 | 20 |  | Planned | Slack 18: 3,5
Intermittent Integration | 7 | 3 |  | Planned | Slack 38: 5, 6
Testing | 8 | 3 |  | Planned | Slack 38: 6
Final Product Implementation | 9 | 4 |  | Planned | Slack 41: 4, 7, 8
Extra Work not Within Plan
Total |  | 69
Yingruo Liu
Requirements Collection | 1 | 1 | 1 | Complete | bar: Planned 1
World Design and Finalization | 2 | 2 | 2 | Complete | bar: In Progress 2 to Complete 3
Skeleton/Draft in 3D | 3 | 14 | 4 | In Progress | Slack 4: 2
Visual Refinement | 4 | 12 | 0 | Planned | Slack 18: 3
Programming | 5 | 23 |  | Planned | Slack 18: 3
Testing | 6 | 7 |  | Planned | Slack 39: 5
User Documentation | 7 | 5 |  | Planned | Slack 46: 6
Installation | 8 | 2 |  | Planned | Slack 53: 7
Extra Work not Within Plan |  |  | 3 |  | Slack 58: 8
Total |  |  | 11
Kiran