## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis |  |  | Overhead
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
Blake | 6800 | 2750 | 4050 | 2800 | 50 | 2750 | 1000 | 600 | 400 | 3000 | 1000 | 2000 | 2400 | 1100 | 1300
Lucas | 9300 | 5800 | 3500 | 4800 | 1600 | 3200 | 1000 | 900 | 100 | 3500 | 2200 | 1300 | 2000 | 1200 | 800
Noah | 9300 | 5900 | 3400 | 4800 | 1400 | 3400 | 1000 | 900 | 100 | 3500 | 2500 | 1000 | 2000 | 400 | 1600
Yingruo | 10900 | 6600 | 4300 | 6600 | 2400 | 4200 | 1000 | 900 | 100 | 3300 | 2200 | 1100 | 2800 | 1400 | 1400
Total | 36300 | 21050 | 15250 | 19000 | 5450 | 13550 | 4000 | 3300 | 700 | 13300 | 7900 | 5400 | 9200 | 4100 | 5100
The rate is $100 per hour

## Gantt
Task | Task Number/Duration |  | Time Spent | Status | Planned | In Progress | Complete | Slack
Blake Rude |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Main Menu (initial) | 1 | 1 | 0.5 | In Progress | bar: Planned 1
Setting Menu (initial) | 2 | 1 |  | Planned | bar: In Progress 2 to Slack 17
In Game HUD | 3 | 5 |  | Planned | bar: In Progress 2 to Slack 6
in Game Tooltips | 4 | 5 |  | Planned | Slack 7: 3
Tutorial | 5 | 4 |  | Planned | Slack 12: 4
Main Menu (final) | 6 | 2 |  | Planned | Slack 16: 5
Setting Menu (final) | 7 | 2 |  | Planned | Slack 18: 6, 2
Testing/Improvement | 8 | 5 |  | Planned | Slack 20: 7
Finalization | 9 | 3 |  | Planned | Slack 25: 8
Extra Work not Within Plan |  |  | Check Overhead
Total |  | 28 | 0.5
Lucas Thoms | bar: Planned 1 to Slack 52
Understanding Requirements | 1 | 2 | 2 | Complete | bar: Planned 1 to In Progress 2
Determining Weapon Characteristics | 2 | 2 | 2 | Complete | bar: Planned 1 to In Progress 2
Determining Ammo Characteristics | 3 | 2 | 2 | Complete | bar: Planned 1 to In Progress 2
Gathering Weapon and Ammo Assets | 4 | 4 | 3 | In Progress | Complete 3: 2,3
Programming Weapon Distribution | 5 | 3 | 2 | In Progress | Slack 7: 4
Programming Ammo Distribution | 6 | 3 | 2 | In Progress | Slack 7: 4
Programming Ammo Pickup/Exchange | 7 | 6 | 1 | In Progress | Slack 10: 6
Programming Weapon Loading | 8 | 6 | 2 | In Progress | Slack 16: 5,7
Programming Weapon Firing | 9 | 6 |  | Planned | Slack 22: 8
Programming Weapon Aiming | 10 | 6 |  | Planned | Slack 16: 5
Documentation | 11 | 4 |  | Planned | bar: Planned 1 to Slack 4
Developing Tests | 12 | 4 | bar: Planned 1 to Slack 4
Extra Work not Within Plan |  |  | Check Overhead
Total |  | 48 | 16
Max Icardo
Sound/Music Collection | 1 | 1 |  | planned | bar: Planned 1
Event Decode | 2 | 1 |  | planned | bar: In Progress 2
Audio Control | 3 | 1 |  | planned | Complete 3: 2
Testing | 4 | 2 |  | planned | Slack 4: 3
Merging | 5 | 1 |  | planned | Slack 6: 4
Extra Work not Within Plan |  |  | Check Overhead
Total |  | 6 | 0
Noah Mammen
Diagrams/Planning | 1 | 4 | 4 | Complete | bar: Planned 1 to Slack 4
Research Player/Camera | 2 | 3 | 3 | Complete | bar: Slack 5 to Slack 7
Programming Player | 3 | 10 | 5 | In Progress | Slack 8: 2
Player/Weapon Interaction | 4 | 2 |  | Planned | Slack 18: 3
Modelling | 5 | 3 | 2 | In Progress | bar: Planned 1 to Complete 3
Research AI | 6 | 4 |  | Planned | Slack 4: 5
Programming AI | 7 | 10 |  | Planned | Slack 18: 3,6
Tuning AI | 8 | 3 |  | Planned | bar: Slack 28 to Slack 30
Testing | 9 | 4 |  | Planned | bar: Slack 31 to Slack 34
Integration | 10 | 2 |  | Planned | bar: Slack 35 to Slack 36
Final Touchups/Refinements | 11 | 3 |  | Planned | bar: Slack 37 to Slack 39
Extra Work not Within Plan |  |  | Check Overhead
Total |  | 48 | 14
Yingruo Liu
Requirements Collection | 1 | 1 | 1 | Complete | bar: Planned 1
World Design and Finalization | 2 | 2 | 2 | Complete | bar: In Progress 2 to Complete 3
Skeleton/Draft in 3D | 3 | 14 | 14 | Complete | Slack 4: 2
Visual Refinement | 4 | 12 | 5 | In Progress | Slack 18: 3
Programming | 5 | 23 | 2 | In Progress | Slack 18: 3
Testing | 6 | 7 |  | Planned | Slack 39: 5
User Documentation | 7 | 5 |  | Planned | Slack 46: 6
Installation | 8 | 2 |  | Planned | Slack 53: 7
Extra Work not Within Plan |  |  | Check Overhead |  | Slack 58: 8
Total |  | 66 | 24
Kiran

## Meetings
| Date | Jan 30th | Feb 10th | Feb 12th | Feb 25th
| Purpose | First Meeting | RFP | Champion | Unity Set up
| Hours | 1 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Blake | 6 | ü |  | ü | ü
Lucas | 9 | ü | ü | ü | ü
Noah | 9 | ü | ü | ü | ü
Yingruo | 9 | ü | ü | ü | ü
Total | 33 | 4 | 9 | 12 | 8 | 0 | 0 | 0 | 0 | 0 | 0
ü

## SA
| Task | Predicted(hrs) | spent(hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Blake | A Make RFP | 2 | 0 | bar: 1 to 2
| B Make Champion | 2 | 2 | bar: 1 to 2
| C Meetings for presentation | 10 | 3 | bar: 3 to 13
| D Make team lead presentation | 6 | 2 | bar: 3 to 8
| E Make individual presentation | 5 | 2 | bar: 3 to 7
| FMake Menu | 5 | 1 | bar: 3 to 7
| Subtotal | 30 | 10
Lucas | A Make RFP | 2 | 2 | bar: 1 to 2
| B Make Champion | 2 | 2 | bar: 1 to 2
| C Meetings for presentation | 10 | 3 | bar: 3 to 13
| D Make team lead presentation | 6 | 5 | bar: 3 to 8
| EMake Individual presentation | 5 | 5 | bar: 3 to 7
| F Weapon Research | 10 | 5 | bar: 3 to 13
| Subtotal | 35 | 22
Yingruo
| A Make RFP | 2 | 2 | bar: 1 to 2
| B Make Champion | 2 | 2 | bar: 1 to 2; 7
| C Meetings for presentation | 10 | 3 | bar: 3 to 13
| D Make team lead presentation | 6 | 10 | bar: 3 to 8
| EMake individual presentation | 5 | 0 | bar: 3 to 7
| F 3D Model Research | 8 | 8 | bar: 3 to 10
| Subtotal | 33 | 25
Noah | A Make RFP | 2 | 2 | bar: 1 to 2
| B Make Champion | 2 | 2 | bar: 1 to 2
| c Meetings for presentation | 10 | 3 | bar: 3 to 13
| D Make Team lead presentation | 6 | 5 | bar: 3 to 8
| E Make Individual presentation | 5 | 5 | bar: 3 to 7
| F Research into AI | 10 | 5 | bar: 3 to 13
| Subtotal | 35 | 22
| Total | 133 | 79
red is dependent on others

## Overhead
Topic | Blake | Lucas | Yingruo | Noah
Training | 5 | 5 | 7 | 6
SA Presentation Prep | 3 | 2 | 3 | 2
Software Specialist Presentation Prep | 5 | 3 | 5 | 3
Team Lead Presentation Prep | 5 | 4 | 5 | 3 | Planned
Oral Exam Prep | 3 | 3 | 5 | 3
Post Mortem Presentation Prep | 3 | 3 | 3 | 3
Total | 24 | 20 | 28 | 20
Topic | Blake | Lucas | Yingruo | Noah
Training | 3 | 3 | 4 | 2
SA Presentation Prep | 2 | 1 | 2 | 2
Software Specialist Presentation Prep | 3 | 3 | 3 | 0 | Actual
Team Lead Presentation Prep | 3 | 5 | 5 | 0
Oral Exam Prep | 0 | 0 | 0 | 0
Post Mortem Presentation Prep | 0 | 0 | 0 | 0
total | 11 | 12 | 14 | 4